## Total
|  | Client: | National MS Society
|  | Campaign: | Bike MS
|  | Reporting Period Through: | 2015-09-24
MARKET | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | CONVERSIONS | CONVERSION RATE | GROSS SPEND | GROSS SPEND REMAINING | CPA
Dallas | 7387073 | 16027 | 0.217% | 60.32% | -8 | 305 | 1.903% | 46799.8063 | 0 | 153.442
Chicago | 9793505 | 39462 | 0.4029% | 86.22% | -3 | 813 | 2.06% | 67528.8618 | 0 | 82.2772
Atlanta | 11657104 | 21601 | 0.1853% | 72.05% | -5 | 234 | 1.083% | 53806.8951 | 7109.1078 | 187.5663
Godfrey | 2925001 | 8121 | 0.2776% | 82.64% | -12 | 100 | 1.231% | 19168.2491 | -1.6191 | 158.3931
Las Vegas | 17218 | 271 | 1.574% | 8.911% | 3 | 10 | 3.69% | 416.0574 | 4343.5226 | 41.6057
Kansas City | 4802972 | 15427 | 0.3212% | 79.38% | -5 | 380 | 2.463% | 30450.1104 | 1217.803 | 66.1556
San Francisco | 4932248 | 15964 | 0.3237% | 85.57% | 2 | 210 | 1.315% | 35307.8845 | -1247.2205 | 138.7926
Total | 41515121 | 116873 | 0.2815% | Varies | Varies | 2052 | 1.756% | 253477.8646 | 11421.5938 | 123.5272

## Total By Platform
|  | Client: | National MS Society
|  | Campaign: | Bike MS
|  | Reporting Period Through: | 2015-09-24
Platform | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | CONVERSIONS | CONVERSION RATE | GROSS SPEND | CPA
Precision | 3771116 | 1443 | 0.03826% | 110 | 7.623% | 28837.9459 | 262.1631
Google Remarketing | 532475 | 785 | 0.1474% | 248 | 31.59% | 5324.75 | 21.4708
Media IQ | 26134600 | 12573 | 0.04811% | 613 | 4.876% | 98318.7559 | 160.3895
Under Armour/MapMyRide | 1944293 | 4674 | 0.2404% | 327 | 6.996% | 21324.0965 | 65.2113
YouTube | 16160 | 0 | 0% | 0 | - | 1000.3765 | -
Facebook | 8094294 | 89702 | 1.108% | 675 | 0.7525% | 76188.7454 | 112.8722
Search | 1004965 | 7425 | 0.7388% | 69 | 0.9293% | 16136.4235 | 233.8612
Display Ad Serving | - | - | - | - | - | 6108.6929 | -
Total | 41497903 | 116602 | 0.281% | 2042 | 1.751% | 253239.7866 | 124.0156

## Dallas
National MS Society
Bike MS - Dallas
| Flight Dates: | 3/2/2015 - 4/25/2015
| Event Dates: | 2015-05-03
| Reporting Through: | 2015-05-11
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | CREATIVE SIZE | COST | PRICING TYPE | EST. RATE | EST. IMPRESSIONS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | CONVERSIONS | Conversion Rate | SPEND | REMAINING | CPA
Precision | Custom List Match | Display Banners | 2015-03-02 | 2015-04-17 | -- | 300x250, 728x90, 160x600, 300x600 | 20000 | CPM | 7.6471 | 2615384.6154 | 1659757 | 483 | 0.0291% | 63.46% | -8 | 27 | 5.59% | 12692.2594 | 7307.7406 | 470.0837
Precision | Cycling/Fitness Enthusiasts | Display Banners | 2015-04-13 | 2015-04-17 | -- | 300x250, 728x90, 160x600, 300x600 | 6000 | CPM | 7.6471 | 784615.3846 | 447781 | 96 | 0.02144% | 57.07% | -8 | 7 | 7.292% | 3424.2076 | 2575.7924 | 489.1725
Google Remarketing | Remarketing to Users who Visited the Bike MS Website and did not sign up | Display Banners | 2015-03-02 | 2015-04-17 | -- | 300x250, 728x90, 160x600, 300x600 | 1163 | CPM | 10 | 116300 | 92921 | 130 | 0.1399% | 79.9% | -8 | 49 | 37.69% | 929.21 | 233.79 | 18.9635
Media IQ | Cycling Enthusiasts | Display Banners | 2015-03-02 | 2015-04-17 | -- | 300x250, 728x90, 160x600, 300x600 | 17647.0588 | CPM | 2.9412 | 6000000 | 2754969 | 2103 | 0.07633% | 45.92% | -8 | 39 | 1.854% | 8102.85 | 9544.2088 | 207.7654
Media IQ | Fitness Enthusiasts | Display Banners | 2015-03-02 | 2015-04-17 | -- | 300x250, 728x90, 160x600, 300x600 | 10435.2941 | CPM | 2.9412 | 3548000 | 1224938 | 784 | 0.064% | 34.52% | -8 | 15 | 1.913% | 3602.7588 | 6832.5353 | 240.1839
Under Armour/MapMyRide | Cycling Enthusiasts | Email | 2015-03-30 | 2015-03-30 | -- | 640x300 Hero Header | 1411.7647 | Per Email | 0.070588 | 20000 | 20676 | 159 | 0.769% | 100% | -8 | 0 | 0% | 1411.7647 | 0 | --
Under Armour/MapMyRide | Cycling Enthusiasts | Email | 2015-04-13 | 2015-04-13 | -- | 640x300 Hero Header | 1411.7647 | Per Email | 0.070588 | 20000 | 25438 | 89 | 0.3499% | 100% | -8 | 0 | 0% | 1411.7647 | 0 | --
Under Armour/MapMyRide | Cycling Enthusiasts | Mobile Intersitial | 2015-03-16 | 2015-04-17 | -- | 320x480 | 28.2353 | CPM | 18.8235 | 1500 | 1752 | 83 | 4.737% | 116.8% | -8 | 0 | 0% | 32.9788 | -4.7435 | --
Under Armour/MapMyRide | Cycling Enthusiasts | Web Intersitial | 2015-03-16 | 2015-04-17 | -- | 600x480 | 97.0588 | CPM | 12.9412 | 7500 | 7364 | 21 | 0.2852% | 98.19% | -8 | 0 | 0% | 95.2988 | 1.76 | --
Under Armour/MapMyRide | Cycling Enthusiasts | Mobile Banner | 2015-03-16 | 2015-04-17 | -- | 320x50, 360x50 | 1235.2941 | CPM | 17.6471 | 70000 | 70013 | 163 | 0.2328% | 100% | -8 | 0 | 0% | 1235.5235 | -0.22941 | --
Under Armour/MapMyRide | Cycling Enthusiasts | Display Banners | 2015-03-02 | 2015-04-17 | -- | 728x90, 300x250 | 0 | ADDED VALUE | - | 150000 | 150047 | 110 | 0.07331% | -- | -8 | 21 | 19.09% | 0 | 0 | 0
YouTube | Cycling/Fitness Enthusiasts | Preroll Video | 2015-03-02 | 2015-04-17 | -- | :15 | 1000 | CPV | 2.9412 | 26666.6667 | 16160 | -- | -- | 100% | -8 | 0 | -- | 1000.3765 | -0.37647 | --
SUBTOTALS: | [6 empty] | 60429.4706 | Varies | Varies | 13359966.6667 | 6471816 | 4221 | 0.06522% | 56.16% | -8 | 158 | 3.743% | 33938.9929 | 26490.4776 | 214.8038
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE |  | CREATIVE SIZE | COST | PRICING TYPE | EST. RATE | EST. CLICKS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | CONVERSIONS | Conversion Rate | SPEND | REMAINING | CPA
Search | People Searching for National MS Society, Terms Related to MS, Charitable Organizations | Search Results | 2015-01-27 | 2015-04-22 | -- | Search Ads | 3500 | CPC | 2.0761 | 1685.8333 | 362734 | 3152 | 0.869% | 84.93% | -8 | 6 | 0.1904% | 2972.6588 | 527.3412 | 495.4431
Facebook | Custom List Match - Past Participants | Desktop/Mobile | 2015-01-27 | 2015-04-22 | -- | Website Conversions, Video | 400 | CPC | 3.4588 | 115.6463 | 18018 | 318 | 1.765% | 73.35% | -8 | 1 | 0.3145% | 293.384 | 106.616 | 293.384
Facebook | Demographic Match: Male, 22-44, high income, connection to MS, interest in community events | Desktop/Mobile | 2015-01-27 | 2015-04-22 | -- | Website Conversions, Video | 200 | CPC | 3.4602 | 57.8 | 4960 | 175 | 3.528% | 71.24% | -8 | 8 | 4.571% | 142.4791 | 57.5209 | 17.8099
Facebook | Cycling/Fitness Enthusiasts | Desktop/Mobile | 2015-01-27 | 2015-04-22 | -- | Website Conversions, Video | 9856 | CPC | 3.4602 | 2848.384 | 493672 | 6812 | 1.38% | 62.79% | -8 | 29 | 0.4257% | 6188.28 | 3667.72 | 213.389
Facebook | Remarketing to users who visited the website | Desktop/Mobile | 2015-01-27 | 2015-04-25 | -- | Website Conversions, Video | 1000 | CPC | 3.4602 | 289 | 35873 | 1349 | 3.76% | 106.6% | -8 | 103 | 7.635% | 1066.0114 | -66.0114 | 10.3496
SUBTOTALS: | [6 empty] | 14956 | Varies | Varies | 4996.6636 | 915257 | 11806 | 1.29% | 71.29% | -8 | 147 | 1.245% | 10662.8134 | 4293.1866 | 72.5361
[6 empty] | Advanced Metrics Ad Serving | 2198 | [9 empty] | Display Ad Serving: | 2198
[6 empty] | TOTALS: | 77583.4706 | Varies | Varies | 13364963.3303 | 7387073 | 16027 | 0.217% | 60.32% | -8 | 305 | 1.903% | 46799.8063 | 30783.6643 | 153.442

## Chicago
National MS Society
| Bike MS: | Chicago
| Flight Dates: | 2/2/2015 - 6/26/2015
| Event Date: | 2015-06-28
| Reporting Through: | 2015-07-01
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | CREATIVE SIZE | COST | PRICING TYPE | EST. RATE | EST. IMPRESSIONS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | CLICK-THROUGH CONVERSIONS | VIEW-THROUGH CONVERSIONS | TOTAL CONVERSIONS | Conversion Rate | SPEND | REMAINING | CPA
Precision | Custom List Match | Display Banners | 2015-03-02 | 2015-06-12 | 118.6% | 300x250, 728x90, 160x600, 300x600 | 6012 | CPM | 7.6471 | 786184.6154 | 792235 | 394 | 0.04973% | 100.8% | -3 | 1 | 40 | 41 | 10.41% | 6058.2676 | -46.2676 | 147.7626
Precision | Cycling/Fitness Enthusiasts | Display Banners | 2015-04-13 | 2015-06-12 | 131.7% | 300x250, 728x90, 160x600, 300x600 | 647.16 | CPM | 7.6471 | 84628.6154 | 84629 | 39 | 0.04608% | 100% | -3 | 0 | 2 | 2 | 5.128% | 647.1629 | -0.0029412 | 323.5815
Google Remarketing | Remarketing to Users who Visited the Bike MS Website and did not sign up | Display Banners | 2015-03-02 | 2015-06-12 | 118.6% | 300x250, 728x90, 160x600, 300x600 | 1852.84 | CPM | 10 | 185284 | 188754 | 237 | 0.1256% | 101.9% | -3 | 2 | 57 | 59 | 24.89% | 1887.54 | -34.7 | 31.9922
Media IQ | Cycling Enthusiasts | Display Banners | 2015-05-04 | 2015-06-20 | 123.4% | 300x250, 728x90, 160x600, 300x600 | 10000 | CPM | 2.9412 | 3400000 | 3284040 | 1571 | 0.04784% | 96.59% | -3 | 2 | 82 | 84 | 5.347% | 9658.9412 | 341.0588 | 114.9874
Media IQ | Fitness Enthusiasts | Display Banners | 2015-05-04 | 2015-06-20 | 123.4% | 300x250, 728x90, 160x600, 300x600 | 8955.2941 | CPM | 2.9412 | 3044800 | 2904532 | 1321 | 0.04548% | 95.39% | -3 | 2 | 82 | 84 | 6.359% | 8542.7412 | 412.5529 | 101.6993
Under Armour/MapMyRide | Cycling Enthusiasts | Email | 2015-03-30 | 2015-03-30 | -- | 640x300 Hero Header | 1411.7647 | Per Email | 0.070588 | 20000 | 25438 | 439 | 1.726% | 100% | -3 | 0 | 0 | 0 | 0% | 1411.7647 | 0 | --
Under Armour/MapMyRide | Cycling Enthusiasts | Email | 2015-04-20 | 2015-04-20 | -- | 640x300 Hero Header | 1411.7647 | Per Email | 0.070588 | 20000 | 26098 | 431 | 1.651% | 100% | -3 | 1 | 0 | 1 | 0.232% | 1411.7647 | 0 | 1411.7647
Under Armour/MapMyRide | Cycling Enthusiasts | Mobile Intersitial | 2015-03-16 | 2015-06-26 | 104.9% | 320x480 | 47.0588 | CPM | 18.8235 | 2500 | 1659 | 30 | 1.808% | 66.36% | -3 | 5 | 0 | 5 | 16.67% | 31.2282 | 15.8306 | 6.2456
Under Armour/MapMyRide | Cycling Enthusiasts | Web Intersitial | 2015-03-16 | 2015-06-26 | 104.9% | 600x480 | 517.6471 | CPM | 12.9412 | 40000 | 32353 | 5 | 0.01545% | 80.88% | -3 | 1 | 4 | 5 | 100% | 418.6859 | 98.9612 | 83.7372
Under Armour/MapMyRide | Cycling Enthusiasts | Mobile Banners | 2015-03-16 | 2015-05-04 | 218.4% | 320x50, 360x50 | 1076.4706 | CPM | 17.6471 | 61000 | 134983 | 153 | 0.1133% | 221.3% | -3 | 1 | 0 | 1 | 0.6536% | 2382.0529 | -1305.5824 | 2382.0529
Under Armour/MapMyRide | Cycling Enthusiasts | Display Banners | 2015-05-04 | 2015-06-26 | 109.4% | 728x90, 300x250 | 1403.5294 | CPM | 10.5882 | 132555.5556 | 117994 | 59 | 0.05% | 89.01% | -3 | 0 | 10 | 10 | 16.95% | 1249.3482 | 154.1812 | 124.9348
Under Armour/MapMyRide | Cycling Enthusiasts | Display Banners | 2015-03-02 | 2015-06-26 | 104.3% | 728x90, 300x250 | 0 | ADDED VALUE | - | 150000 | 144111 | 89 | 0.06176% | -- | -3 | 4 | 19 | 23 | 25.84% | Added Value | -- | --
SUBTOTALS: | [6 empty] | 33335.5294 | Varies | Varies | 7926952.7863 | 7736826 | 4768 | 0.06163% | 101.1% | -3 | 19 | 296 | 315 | 6.607% | 33699.4976 | -363.9682 | 106.9825
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE |  | CREATIVE SIZE | COST | PRICING TYPE | EST. RATE | EST. CLICKS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | CLICK-THROUGH CONVERSIONS | VIEW-THROUGH CONVERSIONS | TOTAL CONVERSIONS | Conversion Rate | SPEND | REMAINING | CPA
Search | People Searching for National MS Society, Terms Related to MS, Charitable Organizations | Search Results | 2015-02-02 | 2015-06-26 | 103.5% | Search Ads | 9800 | CPC | 2.0761 | 4720.3333 | 144675 | 1590 | 1.099% | 46.84% | -3 | 39 | 0 | 39 | 2.453% | 4590.0353 | 5209.9647 | 117.6932
Facebook | Custom List Match - Past Participants | Desktop/Mobile | 2015-02-02 | 2015-06-26 | 103.5% | Website Conversions, Video | 10161 | CPC | 3.4588 | 2937.7041 | 1061175 | 19601 | 1.847% | 154.8% | -3 | 28 | 47 | 75 | 0.3826% | 15728.9579 | -5567.9579 | 209.7194
Facebook | Demographic Match: Male, 22-44, high income, connection to MS, interest in community events | Desktop/Mobile | 2015-02-02 | 2015-06-26 | 103.5% | Website Conversions, Video | 5233 | CPC | 3.4602 | 1512.337 | 298620 | 3951 | 1.323% | 69.85% | -3 | 16 | 13 | 29 | 0.734% | 3655.1276 | 1577.8724 | 126.0389
Facebook | Cycling/Fitness Enthusiasts | Desktop/Mobile | 2015-02-02 | 2015-06-26 | 103.5% | Website Conversions, Video | 12625 | CPC | 3.4602 | 3648.625 | 351089 | 6016 | 1.714% | 37.93% | -3 | 5 | 17 | 22 | 0.3657% | 4788.9139 | 7836.0861 | 217.6779
Facebook | Remarketing to users who visited the website | Desktop/Mobile | 2015-02-02 | 2015-06-26 | 103.5% | Website Conversions, Video | 5233 | CPC | 3.4602 | 1512.337 | 201120 | 3536 | 1.758% | 74% | -3 | 120 | 213 | 333 | 9.417% | 3872.2865 | 1360.7135 | 11.6285
SUBTOTALS: | [6 empty] | 43052 | Varies | Varies | 14331.3364 | 2056679 | 34694 | 1.687% | 75.8% | -3 | 208 | 290 | 498 | 1.435% | 32635.3212 | 10416.6788 | 65.5328
[6 empty] | Ad Serving | 1194.0429 | [11 empty] | Ad Serving | 1194.0429
[6 empty] | TOTALS: | 77583.2008 | Varies | Varies | 7941284.1227 | 9793505 | 39462 | 0.4029% | 86.22% | -3 | 227 | 586 | 813 | 2.06% | 67528.8618 | 10691.8719 | 82.2772

## Godfrey
National MS Society
| Bike MS: | Godfrey
| Flight Dates: | 7/17/15 - 9/5/2015
| Event Date: | 2015-09-12
| Reporting Through: | 2015-09-24
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | GROSS COST | NET COST | PRICING TYPE | EST. RATE | EST. IMPRESSIONS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | TOTAL CONVERSIONS | CONVERSION RATE | GROSS SPEND | NET SPEND | GROSS SPEND REMAINING | GROSS CPA
Precision | Custom List Match | Display Banners | 2015-07-20 | 2015-09-05 | 140.4% | 0.39 | 0.3315 | CPM | 7.6471 | 230769.2308 | 55 | 8 | 14.55% | 91.67% | -12 | 0 | 0% | 0.42059 | 0.3575 | -0.030588 | --
Google Remarketing | Remarketing to Users who Visited the Bike MS Website and did not sign up | Display Banners | 2015-07-20 | 2015-09-05 | 140.4% | 131.84 | 112.064 | CPM | 10 | 117647 | 13194 | 36 | 0.2729% | 85.06% | -12 | 2 | 5.556% | 131.94 | 112.149 | -0.1 | 65.97
Media IQ | Cycling Enthusiasts | Display Banners | 2015-07-20 | 2015-09-05 | 140.4% | 10754.79 | 9141.5715 | CPM | 5.8824 | 1364000 | 1828527 | 760 | 0.04156% | 85.01% | -12 | 45 | 5.921% | 10756.0412 | 9142.635 | -1.2512 | 239.0231
Under Armour/MapMyRide | Cycling/Fitness Enthusiasts | Desktop ROS Banners | 2015-07-20 | 2015-09-05 | 140.4% | 2325.84 | 1976.964 | CPM | 10.5882 | 222222.2222 | 219663 | 219 | 0.0997% | 85% | -12 | 17 | 7.763% | 2325.8435 | 1976.967 | -0.0035294 | 136.8143
SUBTOTALS: | [5 empty] | 13212.86 | 11230.931 | Varies | Varies | 1934638.453 | 2061439 | 1023 | 0.04963% | 0% | -12 | 64 | 6.256% | 13214.2453 | 11232.1085 | -1.3853 | 206.4726
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | GROSS COST | NET COST | PRICING TYPE | EST. RATE | EST. CLICKS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | TOTAL CONVERSIONS | CONVERSION RATE | GROSS SPEND | NET SPEND | GROSS SPEND REMAINING | GROSS CPA
Search | People Searching for National MS Society, Terms Related to MS, Charitable Organizations | Keyword Targeted Ads | 2015-07-17 | 2015-09-05 | 138% | 445.92 | 379.032 | CPC | 2.0761 | 214.7848 | 12770 | 133 | 1.042% | 85% | -12 | 9 | 6.767% | 445.9176 | 379.03 | 0.0023529 | 42.1144
Facebook | Custom List Match - Past Participants | Targeted Facebook Ads | 2015-07-17 | 2015-09-05 | 138% | 0 | 0 | CPC | 3.4588 | 0 | 11 | 0 | 0% | -- | -12 | 0 | -- | 0.23303 | 0.19 | -0.23303 | --
Facebook | Outdoor/Active Interests | Targeted Facebook Ads | 2015-08-11 | 2015-09-12 | 137.5% | 1565.2 | 1263.899 | CPC | 3.4588 | 452.5238 | 235984 | 2583 | 1.095% | 81.53% | -12 | 10 | 0.3871% | 1565.1972 | 1276.18 | 0.0027647 | 127.618
Facebook | Donation & Purchasing Behaviors | Targeted Facebook Ads | 2015-08-11 | 2015-09-12 | 137.5% | 1557.46 | 1257.6489 | CPC | 3.4588 | 450.2861 | 304442 | 1476 | 0.4848% | 81.53% | -12 | 1 | 0.06775% | 1557.4582 | 1269.87 | 0.0017941 | 1269.87
Facebook | Demographic Match: Male, 22-44, high income, connection to MS, interest in community events | Targeted Facebook Ads | 2015-07-17 | 2015-09-05 | 138% | 315.85 | 255.0489 | CPC | 3.4602 | 91.2807 | 12172 | 215 | 1.766% | 81.54% | -12 | 8 | 3.721% | 315.853 | 257.53 | -0.0029706 | 32.1912
Facebook | Cycling/Fitness Enthusiasts | Targeted Facebook Ads | 2015-07-17 | 2015-09-05 | 138% | 1746.98 | 1410.6863 | CPC | 3.4602 | 504.8772 | 298183 | 2691 | 0.9025% | 81.53% | -12 | 8 | 0.2973% | 1746.9847 | 1424.4 | -0.0047059 | 178.05
Facebook | Remarketing to userse who visited the website | Targeted Facebook Ads | 2015-07-17 | 2015-09-05 | 138% | 0 | 0 | CPC | 3.4602 | 0 | 0 | 0 | -- | -- | -12 | 0 | -- | 0 | 0 | 0 | --
SUBTOTALS: | [5 empty] | 5631.41 | 4566.3152 | Varies | Varies | 1713.7525 | 863562 | 7098 | 0.8219% | 81.81% | -12 | 36 | 0.5072% | 5631.6438 | 4607.2 | -0.23379 | 127.9778
[5 empty] | Advanced Metrics Ad Serving | 322.36 | [11 empty] | 322.36
[6 empty] | 19166.63 | 15797.2462 | Varies | Varies | 1936352.2055 | 2925001 | 8121 | 0.2776% | 82.64% | -12 | 100 | 1.231% | 19168.2491 | 15839.3085 | -1.6191 | 158.3931

## Kansas City
National MS Society
| Bike MS: | Kansas City
| Flight Dates: | 7/17/15 - 9/12/2015
| Event Date: | 2015-09-19
| Reporting Through: | 2015-09-24
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | GROSS COST | NET COST | PRICING TYPE | EST. RATE | EST. IMPRESSIONS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | TOTAL CONVERSIONS | CONVERSION RATE | GROSS SPEND | NET SPEND | GROSS SPEND REMAINING | GROSS CPA
Precision | Custom List Match | Display Banners | 2015-07-20 | 2015-09-12 | 122.2% | 58.82 | 49.997 | CPM | 7.6471 | 230769.2308 | 166 | 29 | 17.47% | 1.834% | -5 | 0 | 0% | 1.2694 | 1.079 | 57.5506 | --
Google Remarketing | Remarketing to Users who Visited the Bike MS Website and did not sign up | Display Banners | 2015-07-20 | 2015-09-12 | 122.2% | 941.18 | 800.003 | CPM | 10 | 117647 | 79655 | 125 | 0.1569% | 71.94% | -5 | 51 | 40.8% | 796.55 | 677.0675 | 144.63 | 15.6186
Media IQ | Cycling Enthusiasts | Display Banners | 2015-07-20 | 2015-09-12 | 122.2% | 15309.49 | 13013.0665 | CPM | 5.8824 | 1364000 | 2709184 | 1502 | 0.05544% | 88.48% | -5 | 97 | 6.458% | 15936.3765 | 13545.92 | -626.8865 | 164.2925
Under Armour/MapMyRide | Cycling/Fitness Enthusiasts | Desktop ROS Banners | 2015-07-20 | 2015-09-12 | 122.2% | 3102.94 | 2637.499 | CPM | 10.5882 | 222222.2222 | 222222 | 143 | 0.06435% | 64.45% | -5 | 203 | 142% | 2352.9388 | 1999.998 | 750.0012 | 11.5908
SUBTOTALS: | [5 empty] | 19412.43 | 16500.5655 | Varies | Varies | 1934638.453 | 3011227 | 1799 | 0.05974% | 83.58% | -5 | 351 | 19.51% | 19087.1347 | 16224.0645 | 325.2953 | 54.3793
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | GROSS COST | NET COST | PRICING TYPE | EST. RATE | EST. CLICKS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | TOTAL CONVERSIONS | CONVERSION RATE | GROSS SPEND | NET SPEND | GROSS SPEND REMAINING | GROSS CPA
Search | People Searching for National MS Society, Terms Related to MS, Charitable Organizations | Keyword Targeted Ads | 2015-07-17 | 2015-09-12 | 121.1% | 3690.3333 | 3136.7833 | CPC | 2.0761 | 1777.5106 | 16903 | 158 | 0.9347% | 11.31% | -5 | 2 | 1.266% | 490.9529 | 417.31 | 3199.3804 | 208.655
Facebook | Custom List Match - Past Participants | Targeted Facebook Ads | 2015-07-17 | 2015-09-12 | 121.1% | 122.65 | 99.0399 | CPC | 3.4588 | 35.46 | 435 | 1 | 0.2299% | 0.8398% | -5 | 0 | 0% | 1.2633 | 1.03 | 121.3867 | --
Facebook | Outdoor/Active Interests | Targeted Facebook Ads | 2015-08-11 | 2015-09-12 | 137.5% | 2170 | 1752.275 | CPC | 3.4588 | 627.381 | 612836 | 4600 | 0.7506% | 127.6% | -5 | 6 | 0.1304% | 3395.3612 | 2768.4 | -1225.3612 | 461.4
Facebook | Donation & Purchasing Behaviors | Targeted Facebook Ads | 2015-08-11 | 2015-09-12 | 137.5% | 2170 | 1752.275 | CPC | 3.4588 | 627.381 | 457056 | 3099 | 0.678% | 109.2% | -5 | 4 | 0.1291% | 2905.5088 | 2369 | -735.5088 | 592.25
Facebook | Demographic Match: Male, 22-44, high income, connection to MS, interest in community events | Targeted Facebook Ads | 2015-07-17 | 2015-09-12 | 121.1% | 412.09 | 332.7627 | CPC | 3.4602 | 119.094 | 25038 | 601 | 2.4% | 81.54% | -5 | 9 | 1.498% | 412.0941 | 336 | -0.0041176 | 37.3333
Facebook | Cycling/Fitness Enthusiasts | Targeted Facebook Ads | 2015-07-17 | 2015-09-12 | 121.1% | 2831 | 2286.0325 | CPC | 3.4602 | 818.159 | 679011 | 5164 | 0.7605% | 106% | -5 | 7 | 0.1356% | 3679.4118 | 3000 | -848.4118 | 428.5714
Facebook | Remarketing to users who visited the website | Targeted Facebook Ads | 2015-07-17 | 2015-09-12 | 121.1% | 409.64 | 330.7843 | CPC | 3.4602 | 118.386 | 466 | 5 | 1.073% | 5.695% | -5 | 1 | 20% | 28.6136 | 23.33 | 381.0264 | 23.33
SUBTOTALS: | [5 empty] | 11805.7133 | 9689.9527 | Varies | Varies | 4123.3715 | 1791745 | 13628 | 0.7606% | 75.51% | -5 | 29 | 0.2128% | 10913.2056 | 8915.07 | 892.5077 | 307.4162
[5 empty] | Advanced Metrics Ad Serving | 449.77 | [11 empty] | 449.77
[6 empty] | 31667.9133 | 26190.5182 | Varies | Varies | 1938761.8245 | 4802972 | 15427 | 0.3212% | 79.38% | -5 | 380 | 2.463% | 30450.1104 | 25139.1345 | 1217.803 | 66.1556

## Las Vegas
National MS Society
| Bike MS: | Las Vegas
| Flight Dates: | 9/4/15 - 9/12/15
| Event Date: | 2015-09-19
| Reporting Through: | 2015-09-16
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | GROSS COST | NET COST | PRICING TYPE | EST. RATE | EST. CLICKS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | TOTAL CONVERSIONS | CONVERSION RATE | GROSS SPEND | NET SPEND | GROSS SPEND REMAINING | GROSS CPA
Search | People Searching for National MS Society, Terms Related to MS, Charitable Organizations | Keyword Targeted Ads | 2015-09-04 | 2015-09-12 | 1050 | 892.5 | CPC | 2.0761 | 505.75 | 3209 | 58 | 1.807% | 24.37% | 3 | 4 | 6.897% | 255.9294 | 217.54 | 794.0706 | 63.9824
Facebook | Custom List Match - Past Participants | Targeted Facebook Ads | 2015-09-04 | 2015-09-12 | 100 | 80.75 | CPC | 3.4588 | 28.9116 | 0 | 0 | -- | #VALUE! | 3 | 0 | -- | -- | -- | -- | --
Facebook | Outdoor/Active Interests | Targeted Facebook Ads | 2015-09-04 | 2015-09-12 | 1050 | 847.875 | CPC | 3.4588 | 303.5714 | 4510 | 47 | 1.042% | 4.363% | 3 | 0 | 0% | 45.3671 | 36.99 | 1004.6329 | --
Facebook | Donation & Purchasing Behaviors | Targeted Facebook Ads | 2015-09-04 | 2015-09-12 | 405.58 | 327.5058 | CPC | 3.4588 | 117.2595 | 1170 | 15 | 1.282% | 2.974% | 3 | 0 | 0% | 11.9458 | 9.74 | 393.6342 | --
Facebook | Demographic Match: Male, 22-44, high income, connection to MS, interest in community events | Targeted Facebook Ads | 2015-09-04 | 2015-09-12 | 834 | 673.455 | CPC | 3.4602 | 241.026 | 1846 | 94 | 5.092% | 4.796% | 3 | 4 | 4.255% | 39.615 | 32.3 | 794.385 | 9.9037
Facebook | Cycling/Fitness Enthusiasts | Targeted Facebook Ads | 2015-09-04 | 2015-09-12 | 1220 | 985.15 | CPC | 3.4602 | 352.58 | 6483 | 57 | 0.8792% | 5.231% | 3 | 2 | 3.509% | 63.2 | 51.53 | 1156.8 | 31.6
Facebook | Remarketing to userse who visited the website | Targeted Facebook Ads | 2015-09-04 | 2015-09-12 | 200 | 161.5 | CPC | 3.4602 | 57.8 | 0 | 0 | -- | 0% | 3 | 0 | -- | 0 | 0 | 200 | --
SUBTOTALS: |  |  |  |  | 4859.58 | 3968.7359 | Varies | Varies | 1606.8985 | 17218 | 271 | 1.574% | 8.911% | 3 | 10 | 3.69% | 416.0574 | 353.6488 | 4343.5226 | 41.6057
[5 empty] | 4859.58 | 3968.7359 | Varies | Varies | 1606.8985 | 17218 | 271 | 1.574% | 8.911% | 3 | 10 | 3.69% | 416.0574 | 353.6488 | 4343.5226 | 41.6057

## Atlanta
National MS Society
| Bike MS: | Atlanta
| Flight Dates: | 4/7/2015 - 9/12/2015
| Event Date: | 2015-09-19
| Reporting Through: | 2015-09-24
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | CREATIVE SIZE | GROSS COST | NET COST | PRICING TYPE | EST. RATE | EST. IMPRESSIONS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | TOTAL CONVERSIONS | CONVERSION RATE | GROSS SPEND | NET SPEND | GROSS SPEND REMAINING | CPA
Precision | Custom List Match | Display Banners | 2015-05-01 | 2015-09-18 | 104.3% | 300x250, 728x90, 160x600, 300x600 | 6012 | 5110.2 | CPM | 7.6471 | 786184.6154 | 786436 | 386 | 0.04908% | 85.03% | -5 | 33 | 8.549% | 6013.9224 | 5111.834 | -1.9224 | 154.9041
Google Remarketing | Remarketing to Users who Visited the Bike MS Website and did not sign up | Display Banners | 2015-05-01 | 2015-09-18 | 104.3% | 300x250, 728x90, 160x600, 300x600 | 1800 | 1530 | CPM | 10 | 180000 | 39759 | 130 | 0.327% | 18.78% | -5 | 3 | 2.308% | 397.59 | 337.9515 | 1402.41 | 112.6505
Media IQ | Cycling Enthusiasts | Display Banners | 2015-06-01 | 2015-09-18 | 105.5% | 300x250, 728x90, 160x600, 300x600 | 14861.1765 | 12632 | CPM | 2.9412 | 4294880 | 5332011 | 2220 | 0.04164% | 89.7% | -5 | 104 | 4.685% | 15682.3853 | 13330.0275 | -821.2088 | 128.1733
Media IQ | Fitness Enthusiasts | Display Banners | 2015-06-01 | 2015-09-18 | 105.5% | 300x250, 728x90, 160x600, 300x600 | 9941.1765 | 8450 | CPM | 2.9412 | 2873000 | 3340333 | 1321 | 0.03955% | 84% | -5 | 69 | 5.223% | 9824.5088 | 8350.8325 | 116.6676 | 121.0266
Under Armour/MapMyRide | Cycling Enthusiasts | Email | 2015-06-15 | 2015-06-16 | -- | 640x300 Hero Header | 1411.7647 | 1200 | Per Email | 0.070588 | 20000 | -- | 292 | -- | -- | -5 | 2 | 0.6849% | - | - | -- | --
Under Armour/MapMyRide | Cycling Enthusiasts | Email | 2015-07-20 | 2015-07-21 | -- | 640x300 Hero Header | 1411.7647 | 1200 | Per Email | 0.070588 | 20000 | -- | 140 | -- | -- | -5 | 0 | 0% | - | - | -- | --
Under Armour/MapMyRide | Cycling Enthusiasts | Mobile Intersitial | 2015-05-01 | 2015-09-18 | 104.3% | 320x480 | 764.7059 | 650 | CPM | 29.4118 | 26000 | 28299 | 1550 | 5.477% | 92.52% | -5 | 1 | 0.06452% | 832.3235 | 707.475 | -67.6176 | 707.475
Under Armour/MapMyRide | Cycling Enthusiasts | Web Intersitial | 2015-05-01 | 2015-09-18 | 104.3% | 600x480 | 647.0588 | 550 | CPM | 12.9412 | 50000 | 48983 | 0 | 0% | 83.27% | -5 | 5 | -- | 633.8976 | 538.813 | 13.1612 | 107.7626
Under Armour/MapMyRide | Cycling Enthusiasts | Mobile Banners | 2015-05-01 | 2015-09-18 | 104.3% | 320x50, 360x50 | 1764.7059 | 1500 | CPM | 17.6471 | 100000 | 98251 | 215 | 0.2188% | 83.51% | -5 | 0 | 0% | 1733.8412 | 1473.765 | 30.8647 | --
Under Armour/MapMyRide | Cycling Enthusiasts | Display Banners | 2015-05-01 | 2015-09-18 | 104.3% | 728x90, 300x250 | 0 | 0 | ADDED VALUE | - | 150000 | 346714 | 145 | 0.04182% | -- | -5 | 4 | 2.759% | - | ADDED VALUE | -- | --
YouTube | Cycling/Fitness Enthusiasts | Preroll Video | TBD | 2015-04-17 | -- | :15 | 1000 | 850 | CPV | 2.9412 | 26666.6667 | -- |  | -- | -- | -5 |  | -- | - | -- | -- | --
SUBTOTALS: | [6 empty] | 39614.3529 | 33672.2 | Varies | Varies | 8526731.2821 | 10020786 | 6399 | 0.06386% | 75.35% | -5 | 221 | 3.454% | 35118.4688 | 29850.6985 | 4495.8841 | 135.071
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | CREATIVE SIZE | GROSS COST | NET COST | PRICING TYPE | EST. RATE | EST. CLICKS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | TOTAL CONVERSIONS | CONVERSION RATE | GROSS SPEND | NET SPEND | GROSS SPEND REMAINING | CPA
Search | People Searching for National MS Society, Terms Related to MS, Charitable Organizations | Search Results | 2015-04-07 | 2015-09-12 | 107.6% | Search Ads | 7364 | 6259.4 | CPC | 2.0761 | 3546.9933 | 379517 | 2030 | 0.5349% | 64.66% | -5 | 13 | -- | 5601.8353 | 4761.56 | 1762.1647 | 366.2738
Facebook | Custom List Match - Past Participants | Desktop/Mobile | 2015-04-07 | 2015-09-12 | 107.6% | Website Conversions, Video | 1577.65 | 1273.9524 | CPC | 3.4588 | 456.1233 | 257 | 0 | 0% | 0% | -5 | 0 | -- | 0 | 0 | 1577.65 | --
Facebook | Outdoor/Active Interests | Targeted Facebook Ads | 2015-08-11 | 2015-09-12 | 137.5% | Website Conversions, Video | 1500 | 1211.25 | CPC | 3.4588 | 433.6735 | 351806 | 5088 | 1.446% | 117.8% | -5 | 0 | 0% | 2167.4556 | 1767.23 | -667.4556 | --
Facebook | Donation & Purchasing Behaviors | Targeted Facebook Ads | 2015-08-11 | 2015-09-12 | 137.5% | Website Conversions, Video | 1500 | 1211.25 | CPC | 3.4588 | 433.6735 | 480035 | 2695 | 0.5614% | 117.8% | -5 | 0 | 0% | 2166.6339 | 1766.56 | -666.6339 | --
Facebook | Demographic Match: Male, 22-44, high income, connection to MS, interest in community events | Desktop/Mobile | 2015-04-07 | 2015-09-12 | 107.6% | Website Conversions, Video | 100 | 80.75 | CPC | 3.4602 | 28.9 | 2438 | 27 | 1.107% | 14.84% | -5 | 0 | 0% | 18.2008 | 14.84 | 81.7992 | --
Facebook | Cycling/Fitness Enthusiasts | Desktop/Mobile | 2015-04-07 | 2015-09-12 | 107.6% | Website Conversions, Video | 7058 | 5699.335 | CPC | 3.4602 | 2039.762 | 422265 | 5362 | 1.27% | 81.18% | -5 | 0 | 0% | 7027.2227 | 5729.63 | 30.7773 | --
Facebook | Remarketing to userse who visited the website | Desktop/Mobile | 2015-04-07 | 2015-09-12 | 107.6% | Website Conversions, Video | 733 | 591.8975 | CPC | 3.4602 | 211.837 | 0 | 0 | -- | 0% | -5 | 0 | -- | 0 | 0 | 733 | --
SUBTOTALS: | [6 empty] | 19832.65 | 16327.8349 | Varies | Varies | 7150.9626 | 1636318 | 15202 | 0.929% | 70.79% | -5 | 13 | 0.08552% | 17219.4263 | 14039.82 | 2613.2237 | 1079.9862
[6 empty] | Ad Serving | 1469 | [10 empty] | Ad Serving | 1469
[6 empty] | TOTALS: | 60916.0029 | 50000.0349 | Varies | Varies | 8533882.2446 | 11657104 | 21601 | 0.1853% | 72.05% | -5 | 234 | 1.083% | 53806.8951 | 43890.5185 | 7109.1078 | 187.5663

## San Francisco
National MS Society
| Bike MS: | San Francisco
| Flight Dates: | 7/17/15 - 9/19/2015
| Event Date: | 2015-09-26
| Reporting Through: | 2015-09-24
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | GROSS COST | NET COST | PRICING TYPE | EST. RATE | EST. IMPRESSIONS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | TOTAL CONVERSIONS | CONVERSION RATE | GROSS SPEND | NET SPEND | GROSS SPEND REMAINING | GROSS CPA
Precision | Custom List Match | Display Banners | 2015-07-20 | 2015-09-19 | 108.2% | 200 | 170 | CPM | 7.6471 | 230769.2308 | 57 | 8 | 14.04% | 0.1852% | 2 | 0 | -- | 0.43588 | 0.3705 | 199.5641 | --
Google Remarketing | Remarketing to Users who Visited the Bike MS Website and did not sign up | Display Banners | 2015-07-20 | 2015-09-19 | 108.2% | 1176.4706 | 1000 | CPM | 10 | 117647 | 118192 | 127 | 0.1075% | 85.39% | 2 | 84 | -- | 1181.92 | 1004.632 | -5.4494 | 14.0705
Media IQ | Cycling Enthusiasts | Display Banners | 2015-07-20 | 2015-09-19 | 108.2% | 15933.02 | 13543.067 | CPM | 5.8824 | 1364000 | 2756066 | 991 | 0.03596% | 86.49% | 2 | 76 | -- | 16212.1529 | 13780.33 | -279.1329 | 213.3178
Under Armour/MapMyRide | Cycling/Fitness Enthusiasts | Desktop ROS Banners | 2015-07-20 | 2015-09-19 | 108.2% | 3352.94 | 2849.999 | CPM | 10.5882 | 222222.2222 | 222235 | 139 | 0.06255% | 59.65% | 2 | 29 | -- | 2353.0765 | 2000.115 | 999.8635 | 81.1406
SUBTOTALS: | [5 empty] | 20662.4306 | 17563.066 | Varies | Varies | 1934638.453 | 3096550 | 1265 | 0.04085% | 81.24% | 2 | 189 | 0% | 19747.5853 | 16785.4475 | 914.8453 | 104.4846
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | GROSS COST | NET COST | PRICING TYPE | EST. RATE | EST. CLICKS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | TOTAL CONVERSIONS | CONVERSION RATE | GROSS SPEND | NET SPEND | GROSS SPEND REMAINING | GROSS CPA
Search | People Searching for National MS Society, Terms Related to MS, Charitable Organizations | Keyword Targeted Ads | 2015-07-17 | 2015-09-19 | 107.8% | 3690.3333 | 3136.7833 | CPC | 2.0761 | 1777.5106 | 88366 | 362 | 0.4097% | 40.98% | 2 | 0 | 0% | 1779.0941 | 1512.23 | 1911.2392 | --
Facebook | Custom List Match - Past Participants | Targeted Facebook Ads | 2015-07-17 | 2015-09-19 | 107.8% | 122.65 | 99.0399 | CPC | 3.4588 | 35.46 | 7325 | 25 | 0.3413% | 41.33% | 2 | 7 | 28% | 62.1698 | 50.69 | 60.4802 | 8.8814
Facebook | Outdoor/Active Interests | Targeted Facebook Ads | 2015-08-11 | 2015-09-19 | 112.8% | 2542 | 2052.665 | CPC | 3.4588 | 734.932 | 463423 | 5066 | 1.093% | 118% | 2 | 3 | 0.05922% | 3678.2466 | 2999.05 | -1136.2466 | 1226.0822
Facebook | Employer Based Targeting | Targeted Facebook Ads | 2015-08-13 | 2015-09-19 | 113.5% | 500 | 403.75 | CPC | 3.4588 | 144.5578 | 159151 | 1069 | 0.6717% | 199.9% | 2 | 0 | 0% | 1225.8696 | 999.51 | -725.8696 | --
Facebook | Donation & Purchasing Behaviors | Targeted Facebook Ads | 2015-08-11 | 2015-09-19 | 112.8% | 2042 | 1648.915 | CPC | 3.4588 | 590.3741 | 519498 | 3012 | 0.5798% | 146.9% | 2 | 2 | 0.0664% | 3679.4118 | 3000 | -1637.4118 | 1839.7059
Facebook | Demographic Match: Male, 22-44, high income, connection to MS, interest in community events | Targeted Facebook Ads | 2015-07-17 | 2015-09-19 | 107.8% | 412.09 | 332.7627 | CPC | 3.4602 | 119.094 | 36257 | 623 | 1.718% | 194% | 2 | 5 | 0.8026% | 980.5755 | 799.51 | -568.4855 | 196.1151
Facebook | Cycling/Fitness Enthusiasts | Targeted Facebook Ads | 2015-07-17 | 2015-09-19 | 107.8% | 3204 | 2587.23 | CPC | 3.4602 | 925.956 | 561678 | 4542 | 0.8086% | 93.63% | 2 | 4 | 0.08807% | 3679.4118 | 3000 | -475.4118 | 919.8529
Facebook | Remarketing to userse who visited the website | Targeted Facebook Ads | 2015-07-17 | 2015-09-19 | 107.8% | 409.64 | 330.7843 | CPC | 3.4602 | 118.386 | 0 | 0 | -- | 0% | 2 | 0 | -- | 0 | 0 | 409.64 | --
SUBTOTALS: | [5 empty] | 12922.7133 | 10591.9302 | Varies | Varies | 4446.2705 | 1835698 | 14699 | 0.8007% | 95.65% | 2 | 21 | 0.1429% | 15084.7792 | 12360.99 | -2162.0658 | 718.3228
[5 empty] | Ad Serving | 475.52 | [11 empty] | 475.52
[6 empty] | 34060.6639 | 28154.9962 | Varies | Varies | 1939084.7235 | 4932248 | 15964 | 0.3237% | 85.57% | 2 | 210 | 1.315% | 35307.8845 | 29146.4375 | -1247.2205 | 138.7926

## Atlanta (7-7-2015) (hidden)
National MS Society
| Bike MS: | Atlanta
| Flight Dates: | 4/7/2015 - 9/18/2015
| Event Date: | 2015-09-20
| Reporting Through: | 2015-07-07
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | CREATIVE SIZE | COST | NET COST | PRICING TYPE | EST. RATE | EST. IMPRESSIONS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | CLICK-THROUGH CONVERSIONS | VIEW-THROUGH CONVERSIONS | TOTAL CONVERSIONS | Conversion Rate | GROSS SPEND | SPEND | REMAINING | CPA
Precision | Custom List Match | Display Banners | 2015-05-01 | 2015-09-18 | 47.86% | 300x250, 728x90, 160x600, 300x600 | 6012 | 5110.2 | CPM | 7.6471 | 786184.6154 | 93655 | 62 | 0.0662% | 11.91% | 75 | 3 | 4 | 7 | 11.29% |  | 716.1853 | 5295.8147 | 102.3122
Google Remarketing | Remarketing to Users who Visited the Bike MS Website and did not sign up | Display Banners | 2015-05-01 | 2015-09-18 | 47.86% | 300x250, 728x90, 160x600, 300x600 | 1800 | 1530 | CPM | 10 | 180000 | 34219 | 61 | 0.1783% | 19.01% | 75 | 0 | 2 | 2 | 3.279% |  | 342.19 | 1457.81 | 171.095
Media IQ | Cycling Enthusiasts | Display Banners | 2015-06-01 | 2015-09-18 | -- | 300x250, 728x90, 160x600, 300x600 | 5861.1765 | 4982 | CPM | 2.9412 | 1992800 | 787309 | 360 | 0.04573% | 39.51% | 75 | 9 | 15 | 24 | 6.667% |  | 2315.6147 | 3545.5618 | 96.4839
Media IQ | Fitness Enthusiasts | Display Banners | 2015-06-01 | 2015-09-18 | -- | 300x250, 728x90, 160x600, 300x600 | 941.1765 | 800 | CPM | 2.9412 | 320000 | 171088 | 91 | 0.05319% | 53.46% | 75 | 1 | 10 | 11 | 12.09% |  | 503.2 | 437.9765 | 45.7455
Under Armour/MapMyFitness | Cycling Enthusiasts | Email | 2015-06-15 | 2015-06-16 | -- | 640x300 Hero Header | 1411.7647 | 1200 | Per Email | 0.070588 | 20000 | -- | 0 | -- | -- | 75 | 0 | 0 | 0 | -- |  | -- | -- | --
Under Armour/MapMyFitness | Cycling Enthusiasts | Email | 2015-07-20 | 2015-07-21 | -- | 640x300 Hero Header | 1411.7647 | 1200 | Per Email | 0.070588 | 20000 | -- | 0 | -- | -- | 75 | 0 | 0 | 0 | -- |  | -- | -- | --
Under Armour/MapMyFitness | Cycling Enthusiasts | Mobile Intersitial | 2015-05-01 | 2015-09-18 | 47.86% | 320x480 | 764.7059 | 650 | CPM | 29.4118 | 26000 | 13934 | 774 | 5.555% | 53.59% | 75 | 1 | 0 | 1 | 0.1292% |  | 409.8235 | 354.8824 | 409.8235
Under Armour/MapMyFitness | Cycling Enthusiasts | Web Intersitial | 2015-05-01 | 2015-09-18 | 47.86% | 600x480 | 647.0588 | 550 | CPM | 12.9412 | 50000 | 10475 | 0 | 0% | 20.95% | 75 | 0 | 2 | 2 | -- |  | 135.5588 | 511.5 | 67.7794
Under Armour/MapMyFitness | Cycling Enthusiasts | Mobile Banners | 2015-05-01 | 2015-09-18 | 47.86% | 320x50, 360x50 | 1764.7059 | 1500 | CPM | 17.6471 | 100000 | 48729 | 93 | 0.1909% | 48.73% | 75 | 0 | 0 | 0 | 0% |  | 859.9235 | 904.7824 | --
Under Armour/MapMyRide | Cycling Enthusiasts | Display Banners | 2015-05-01 | 2015-09-18 | 47.86% | 728x90, 300x250 | 0 | 0 | ADDED VALUE | - | 150000 | 73740 | 13 | 0.01763% | -- | 75 | 0 | 0 | 0 | 0% |  | ADDED VALUE | -- | --
YouTube | Cycling/Fitness Enthusiasts | Preroll Video | TBD | 2015-04-17 | -- | :15 | 1000 | 850 | CPV | 2.9412 | 26666.6667 | -- |  | -- | -- | 75 |  |  |  | -- |  | -- | -- | --
SUBTOTALS: | [6 empty] | 21614.3529 | 18372.2 | Varies | Varies | 3671651.2821 | 1233149 | 1454 | 0.1179% | 24.44% | 75 | 14 | 33 | 47 | 3.232% |  | 5282.4959 | 16331.8571 | 112.3935
SITE/NETWORK | AUDIENCE | PLACEMENT | START DATE | END DATE | Projected Pacing | CREATIVE SIZE | COST | NET COST | PRICING TYPE | EST. RATE | EST. CLICKS | DELIVERED IMPRESSIONS | DELIVERED CLICKS | CTR | ACTUAL PACING | DAYS OUT FROM EVENT | CLICK-THROUGH CONVERSIONS | VIEW-THROUGH CONVERSIONS | TOTAL CONVERSIONS | Conversion Rate |  | NET SPEND | REMAINING | CPA
Search | People Searching for National MS Society, Terms Related to MS, Charitable Organizations | Search Results | 2015-04-07 | 2015-09-18 | 55.49% | Search Ads | 22164 | 18839.4 | CPC | 2.0761 | 10675.66 | 53361 | 605 | 1.134% | 9.095% | 75 | -- | -- | 0 | 0% |  | 2015.8118 | 20148.1882 | --
Facebook | Custom List Match - Past Participants | Desktop/Mobile | 2015-04-07 | 2015-09-18 | 55.49% | Website Conversions, Video | 10161 | 8636.85 | CPC | 3.4588 | 2937.7041 | 190 | 0 | 0% | 0% | 75 | -- | -- | 0 | -- |  | 0 | 10161 | --
Facebook | Demographic Match: Male, 22-44, high income, connection to MS, interest in community events | Desktop/Mobile | 2015-04-07 | 2015-09-18 | 55.49% | Website Conversions, Video | 5233 | 4448.05 | CPC | 3.4602 | 1512.337 | 1906 | 20 | 1.049% | 0.2386% | 75 | -- | -- | 0 | 0% |  | 12.4855 | 5220.5145 | --
Facebook | Cycling/Fitness Enthusiasts | Desktop/Mobile | 2015-04-07 | 2015-09-18 | 55.49% | Website Conversions, Video | 12625 | 10731.25 | CPC | 3.4602 | 3648.625 | 224514 | 2934 | 1.307% | 29.02% | 75 | -- | -- | 0 | 0% |  | 3663.4922 | 8961.5078 | --
Facebook | Remarketing to userse who visited the website | Desktop/Mobile | 2015-04-07 | 2015-09-18 | 55.49% | Website Conversions, Video | 5233 | 4448.05 | CPC | 3.4602 | 1512.337 | 0 | 0 | -- | 0% | 75 | -- | -- | 0 | -- |  | 0 | 5233 | --
SUBTOTALS: | [6 empty] | 55416 | 47103.6 | Varies | Varies | 20286.6631 | 279971 | 3559 | 1.271% | 10.27% | 75 | 0 | 0 | 0 | 0% |  | 5691.7894 | 49724.2106 | --
[6 empty] | Advanced Metrics Ad Serving | 553 | [12 empty] | Display Ad Serving: |  | 13.54
[6 empty] | TOTALS: | 77583.3529 |  | Varies | Varies | 3691937.9451 | 1513120 | 5013 | 0.3313% | 14.16% | 75 | 14 | 33 | 47 | 0.9376% |  | 10987.8253 | 66595.5276 | 233.7835